Sample May Day Event Planning Calendar

Use this sample planning calendar to help “back-map” the steps for your May Day event.

The calendar starts from the day of the NEA Leader & Activist Call, and includes all 8 weeks leading up to May 1, 2026, as well as the weeks after for your de-brief and follow-up planning, too!

Some items are already entered as suggestions, but you should adjust, add your own milestones, deadlines, and tasks. If you need any help figuring out how to make your event a success or the best way to plan out your path to May Day, email action@nea.org

| MARCH2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MONDAY |  | TUESDAY |  |  | WEDNESDAY |  |  |  | THURSDAY |  |  |  | FRIDAY |  |  | SAT/SUN |  |  |  |
|  | 23 |  | 24 |  | 25 |  |  |  | 26 |  |  |  | 27 |  |  |  |  | 28/29 |  |  |  |
| Week 1 |  | Click here to enter text. |  |  |  |  |  |  |  |  | NEA May Day Leader & Activist Call |  |  |  | Form a planning committee and schedule your first meeting. |  |  |  | Planning committee decides event date, time, and location. |  |  |
| ## Notes |  | Click here to enter text. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 30 |  | 31 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Week 2 |  | Create dream list of speakers and begin outreach. Map out your promotion plan, including who are your target audiences. |  | Contact local unions, businesses, non-profits, and other groups who may be interested in partnering with you on this event. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| April2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MONDAY |  | TUESDAY |  |  | WEDNESDAY |  |  |  | THURSDAY |  |  |  | FRIDAY |  |  | SAT/SUN |  |  |  |
|  |  |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  |  | 4/5 |  |  |  |
| WEEK 3 |  | Click here to enter text. |  |  |  |  | Check with officials to determine if you need a permit for your event. |  |  |  | Decide how you are tracking registration and collecting attendee contact information. |  |  |  | Start promotion to potential attendees. |  |  |  | Outreach to community, fellow union members, and parents to participate. |  |  |
| ## Notes |  | Click here to enter text. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 |  | 7 |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  |  | 11/12 |  |  |  |
| WEEK 4 |  | Identify volunteers to help with set up/clean up and other in-person roles for your event. |  |  |  |  |  |  |  |  | Secure a working list of available and interested speakers and begin to create the event run-of-show. |  |  |  | ID photographers and social media point people for event coverage. |  |  |  | Finalize and prep speakers. |  |  |
| ## Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 13 |  | 14 |  | 15 |  |  |  | 16 |  |  |  | 17 |  |  |  |  | 18/19 |  |  |  |
| Week 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | “Canvass” your buildings room-by-room to drive turnout, increase interest and get more volunteers.. |  |  |  | Canvass the neighborhood to drive turnout, increase interest and secure commitments. |  |  |
| ## Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 |  | 21 |  | 22 |  |  |  | 23 |  |  |  | 24 |  |  |  |  | 25/26 |  |  |  |
| Week 6 |  | Draft your media plan and begin outreach to reporters by sending out your media advisory. |  |  |  |  | Send reminder calls, emails & texts to registrants and potential participants. |  |  |  | Pitch media by making direct 1:1 contact with select reporters—call them if possible! |  |  |  | Submit updates on planned event to NEA at action@nea.org. |  |  |  | Do a run-through of the logistics for the event with your planning team. |  |  |
| ## Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 27 |  | 28 |  | 29 |  |  |  | 30 |  |  |  |  |  |  |  |  |  |  |  |  |
| Week 7 |  |  |  | Pitch additional media or reach out to anyone you couldn’t get ahold of by making direct 1:1 contact! |  |  |  |  |  |  | Reminder calls, emails, texts to build turnout. |  |  |  |  |  |  |  |  |  |  |
| ## Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| MAY2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MONDAY |  | TUESDAY |  |  | WEDNESDAY |  |  |  | THURSDAY |  |  |  | FRIDAY |  |  | SAT/SUN |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  | 2/3 |  |  |  |
| WEEK 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Host your event! Remember to work with the press and your communications team to cover the event publicly |  |  |  | Continue to tell your story online and to the media. Share photos, media and highlights w/ NEA at action@nea.org. |  |  |
| ## Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 |  | 5 |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  |  | 9/10 |  |  |  |
| WEEK 9 | Click here to enter text. |  |  | Thank supporters and tell them to stay tuned for more ways to show solidarity . |  |  | Meet with your planning team to debrief and decide on next steps for your movement! |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Notes | Click here to enter text. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 11 |  | 12 |  | 13 |  |  |  | 14 |  |  |  | 15 |  |  |  |  | 16/17 |  |  |  |
| Week 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 18 |  | 19 |  | 20 |  |  |  | 21 |  |  |  | 22 |  |  |  |  | 23/24 |  |  |  |
| Week 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 25 |  | 26 |  | 27 |  |  |  | 28 |  |  |  | 29 |  |  |  |  | 30/31 |  |  |  |
| Week 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ## Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |